## Annual Workplan
DEPARTMENT OF HEALTH
KHYBER PAKHTUNKHWA HUMAN CAPITAL INVESTMENT PROJECT
ANNUAL WORK PLAN FY 2024-25
S.NO |  | Outputs/Activities | Annexures | Codes as per IUFRs | Output Indicators | Geographic Focus | Timeframe |  |  |  | Implementaion Modalities | Budget Detail FY 2024-25 |  |  |  |  | Remarks
[7 empty] | Q1 | Q2 | Q3 | Q4 |  | Targets | Account Codes as per CoA | Total Amount (PKR) | Unit Cost | Total Amount USD (PKR 285 = 1 USD)
1 | 1.3 | HR/Salary Component | A | IOC | Project Director, Deputy Project Director, Procurement Specialist, Financial Management Speciaist, M& E Specialist, MIS officer, 02 Assistants, Accountant and Auxiliary Staff | Peshawar | 11526000 | 11526000 | 11526000 | 11526000 | Hired/Project Staff | 20 | A01- Employ related Expenses | 46104000 | 2305200 | 161768.4211
2 | 1.3 | Non Salary Component | B | IOC | Telephone Charges Gas Charges Electricity Charges Printing Stationary Convence Repair & Maintanance of vehicle TA/DA Confrence Newspaper Entertainment Advertisement & Promotion etc | Peshawar | 15975000 | 15975000 | 15975000 | 15975000 | PMU KP HCIP | 23 | A03- Operating Expenses | 63900000 | 2778260.8696 | 224210.5263
3 | 1.3 | Non Salary Component | B | Trainings and Workshops | Conferences/Seminars/Workshops/Symposia | Peshawar | 1175000 | 1175000 | 1175000 | 1175000 | PMU KP HCIP | 12 | A03- Operating Expenses | 4700000 | 391666.6667 | 16491.2281
4 | 1.3 | Puchase of Plant and Machinery | B | Goods (Tangible and Intangible) | Purchase of Office Equipments | Peshawar |  | 500000 |  | 500000 | PMU KP HCIP | 3 | A-09 Expenditure on acquiring of Physical Assets | 1000000 | 333333.3333 | 3508.7719
5 | 1.3 | Purchase of Furniture and Fixtures | B | Goods (Tangible and Intangible) | Purchase of Furniture and Fixtures | Peshawar |  | 1000000 |  |  | PMU KP HCIP | 3 | A-09 Expenditure on acquiring of Physical Assets | 1000000 | 333333.3333 | 3508.7719
6 | 1.3 | Purchase of Computers | B | Goods (Tangible and Intangible) | Purchase of Computers and Accessories | Peshawar |  | 1000000 |  |  | PMU KP HCIP | 3 | A-09 Expenditure on acquiring of Physical Assets | 1000000 | 333333.3333 | 3508.7719
7 | 1.3 | Purchase of Vehicles | B | Goods (Tangible and Intangible) | Purchase of Motorcycles | Peshawar | 1005000 | 1995000 |  |  | PMU KP HCIP | 3 | A-09 Expenditure on acquiring of Physical Assets | 3000000 | 1000000 | 10526.3158 | 1.3333
8 | 1.3 | PMU, Internal audit, Project M&E, Third Party Monitoring etc. |  | Consulting Firm/Individuals | Hirring of Firm for M&E of Project etc. | Peshawar | 45000000 | 60000000 | 60000000 | 135000000 | PMU KP HCIP | 12 | A037- Consultancy & Contractual work /A094- Other Stores and Stocks | 300000000 | 25000000 | 1052631.5789
9 | 1.1 | Infrastructure and Equipment Upgradation of 24/7 BHUs and RHC (Civil works, Solar power system, Furniture and Equipment) | C | Civil work and Goods (Tangible and Intangible) | Hiring of Design and supervision Firm/Construction Firm/Supplier for Equipment | Haripur, Nowshera, Peshawar & Swabi |  | 1316260000 | 3948780000 | 1316260000 | Consultancy Firm (Design & Supervision) along with supervision of PMU | 9 | A037- Consultancy & Contractual work /A094- Other Stores and Stocks | 6581300000 | 731255555.5556 | 23092280.7018
10 | 1.1 | Provision of Essential Medicines to BHU, RHC, Cat-D & Cat-C of selected distrcits | C | Goods (Tangible and Intangible) | Procurement of Medicines from Firm/Supplier | Haripur, Nowshera, Peshawar & Swabi |  | 1000000000 |  |  | Consultancy Firm along with supervision of PMU | 5 | A094- Other Stores and Stocks | 1000000000 | 200000000 | 3508771.9298 | In PC-1 in year three total USD 1.3 M allocated, however, the amount have been increased upto 3.5 M to cater the need of healthcare facilitie to achieve RF indicators. | 142000000 | 498245.614
11 | 1.1 | Provision of Family Planning comodities to BHU, RHC, Cat-D & Cat-C of selected distrcits | C | Goods (Tangible and Intangible) | Procurement of Family Planning Commodities from Firm/Supplier | Haripur, Nowshera, Peshawar & Swabi |  | 400000000 |  |  | Consultancy Firm along with supervision of PMU | 9 | A094- Other Stores and Stocks | 400000000 | 44444444.4444 | 1403508.7719 | In PC-1 in year three total USD 0.6 M allocated, however, the amount have been increased upto 1.4 M to cater the need of healthcare facilities and RFW indicators.
12 | 1.1 | Support to ensure 24/7 BHU, RHC, Cat-D and Cat-C operation | C | Consulting Services/Contractual Staff Hiring | Hiring of Paramedical Staff through Consultancy Firm | Haripur, Nowshera, Peshawar & Swabi |  | 188034000 | 188034000 | 193732000 | Consultancy Firm along with supervision of PMU | 10 | A037- Consultancy & Contractual work | 569800000 | 56980000 | 1999298.2456 | The amount allocated in PC-1 was 3 M USD, however, as per mutual discussion with WB for cancellation of amount, 1 M USD was proposed for cancellation due to the reason that till June 25, this amount will not be utilized and WB clearly instrcuted that the Project will end by June 25.
13 | 1.1 | Improvement of patient record systems | C | Consulting Services | Hiring of Consultancy Firm | Haripur, Nowshera, Peshawar & Swabi | 57000000 | 171000000 | 342000000 |  | Consultancy Firm along with supervision of PMU | 10 | A037- Consultancy & Contractual work | 570000000 | 57000000 | 2000000
14 | 1.1 | Infrastructure and Equipment upgrading of Category C and D hospitals for referral | C | Civil work and Goods (Tangible and Intangible) | Hiring of Design and supervision Firm/Construction Firm/Supplier for Equipment | Haripur, Nowshera, Peshawar & Swabi |  | 228000000 | 684000000 | 228000000 | Consultancy Firm along with supervision of PMU | 8 | A037- Consultancy & Contractual work /A094- Other Stores and Stocks | 1140000000 | 142500000 | 4000000 | The amount allocated in PC-1 was 9.06 M USD, however, as per mutual discussion with WB for cancellation of amount, 5.06 M USD was proposed for cancellation due to the reason that till June 25, this amount will not be utilized and WB clearly instrcuted that the Project will end by June 25. Moreover, the scope of project was also reduced by WB instruction i.e. from 24 Cat-C and D hospital, the infra work is restrcited to only 04 facilities; however, equipments will be provided.
15 | 1.1 | Hospital waste management for BHU, RHC, Cat-D & Cat-C of selected distrcits | C | Consulting Services and Goods (Tangible and Intangible) | Hiring of Consultancy Firm/Procurement from Firm or supplier | Haripur, Nowshera, Peshawar & Swabi |  |  | 1282500000 | 142500000 | Consultancy Firm along with supervision of PMU | 8 | A037- Consultancy & Contractual work /A094- Other Stores and Stocks | 1425000000 | 178125000 | 5000000 | In PC-1 the total USD 3.75 M allocated, however, the amount have been increased upto 1.25 M to catter the need of healthcare facilities amd RFW.
16 | 1.1 | Warehouses establishement for strengthening the supply chain system strengthening | C | Civil work and Goods (Tangible and Intangible) | Hiring of Design and supervision Firm/Construction Firm/Supplier for Equipment | Peshawar | 142500000 | 142500000 | 142500000 | 142500000 | Consultancy Firm along with supervision of PMU | 6 | A037- Consultancy & Contractual work /A094- Other Stores and Stocks | 570000000 | 95000000 | 2000000
17 | 1.1 | Strengthening of referral system | C | Consulting Services and Goods (Tangible and Intangible) | Hiring of Consultancy Firm/Procurement from Firm or supplier | Haripur, Nowshera, Peshawar & Swabi |  | 142500000 |  |  | Consultancy Firm along with supervision of PMU | 6 | A037- Consultancy & Contractual work /A094- Other Stores and Stocks | 142500000 | 23750000 | 500000
18 | 1.1 | Stregthening of RMNCH Services through purchase of Ambulances | C | Consulting Services and Goods (Tangible and Intangible) | Procurement of Vehicle and/or Hiring of Consultancy Firm | Haripur, Nowshera, Peshawar & Swabi | 1425000000 |  |  |  | Consultancy Firm along with supervision of PMU | 6 | A037- Consultancy & Contractual work /A094- Other Stores and Stocks | 1425000000 | 237500000 | 5000000 | In PC-1 the total USD 4.375 M allocated, however, the amount have been increased upto 0.625 M to catter the need of healthcare facilities amd RFW.
19 | 1.1 | Outsourcing of lab and pharmaceutical services | C | Consulting Services | Hiring of Consultancy Firm | Haripur, Nowshera, Peshawar & Swabi |  | 570000000 |  |  | Consultancy Firm along with supervision of PMU | 6 | A037- Consultancy & Contractual work | 570000000 | 95000000 | 2000000 | In PC-1 in year three total USD 1.5 M allocated, however, the amount have been increased upto 0.375 M and the rest is carry forward to next FY. Only Lab will be outsourced and Pharmacy will not be outsourced due to limited time left in PC-1.
20 | 1.1 | Outsourcing of security and janitorial services | C | Non Consulting Services | Hiring of Non Consultancy Firm | Haripur, Nowshera, Peshawar & Swabi | 117000000 | 175500000 | 175500000 | 182000000 | Consultancy Firm along with supervision of PMU | 10 | A037- Consultancy & Contractual work | 650000000 | 65000000 | 2280701.7544 | IN PC-1; 3 M USD allocated, however, 1 M USD already expended so additional is reapropriated from other heads.
21 | 1.1 | Outsourcing of Government Health facility at Nishtarabad | C | Consulting Services | Hiring of Consultancy Firm | Peshawar | 100000000 | 100000000 | 100000000 | 100000000 | MERF along with supervision of PMU | 12 | A037- Consultancy & Contractual work | 400000000 | 33333333.3333 | 1403508.7719 | The amount allocated in PC-1 was 4.5 M USD, however, as per mutual discussion with WB for cancellation of amount, 2 M USD was proposed for cancellation due to the reason that till June 25, this amount will not be utilized and WB clearly instrcuted that the Project will end by June 25. The process advertised for 03 years, however, now the timeline for contract will be 01 year i.e. till 2025.
22 | 1.1 | Health promotion activities (Health Promoting school and WASH activities) | C | Non Consulting Services and Goods (Tangible and Intangible) | Hiring of Non Consultancy Firm and/or Procurent from Firm/Supplier | Haripur, Nowshera, Peshawar & Swabi |  | 245000000 | 105000000 |  | Consultancy Firm along with supervision of PMU | 12 | A037- Consultancy & Contractual work | 350000000 | 29166666.6667 | 1228070.1754 | In PC 0.7 M USD allocated, however, to achieve RF the amount required is 1.22 M USD. The additional amount is reapriated from other heads.
23 | 1.2 | Training of healthcare providers and capacity building of Health Dept staff | C | Consulting Services | Hiring the Services of PHSA | Haripur, Nowshera, Peshawar & Swabi |  |  | 570000000 |  | PHSA along with supervision of PMU | 12 | A037- Consultancy & Contractual work | 570000000 | 47500000 | 2000000
24 | 1.3 | Quality Enhancement | C | Consulting Services and Goods (Tangible and Intangible) | Hiring of Consultancy Firm/Procurement from Firm or supplier | Haripur, Nowshera, Peshawar & Swabi | 68400000 | 216600000 | 285000000 |  | Consultancy Firm along with supervision of PMU | 12 | A037- Consultancy & Contractual work /A094- Other Stores and Stocks | 570000000 | 47500000 | 2000000
25 | 1.3 | KP Health Care Commission support (Registeration and GIS mapping of all private healthcare establishment across KP) | C | Consulting Services | Hiring of Consultancy Firm | Haripur, Nowshera, Peshawar & Swabi | 5112900 | 3408600 | 8521500 |  | HCC along with supervision of PMU | 12 | A037- Consultancy & Contractual work | 17043000 | 1420250 | 59800
26 | 1.3 | Support to KP-HF for PPP Stregthening | C | Consulting Services | Hiring of Consultancy Firm | Haripur, Nowshera, Peshawar & Swabi | 23856000 | 15904000 | 39760000 |  | HCC along with supervision of PMU | 13 | A037- Consultancy & Contractual work | 79520000 | 6116923.0769 | 279017.5439
27 | 1.3 | TA to support PMU | D | Consulting Services | Hiring of Consultancy Firm/Individuals | Haripur, Nowshera, Peshawar & Swabi | 16038364.125 | 16038364.125 | 16038364.125 | 16038364.125 | PMU KP HCIP | 15 | A037- Consultancy & Contractual work | 64153456.5 | 4276897.1 | 225099.8474 | In PC-1 in year three total USD 0.105 M allocated, however, the amount have been increased upto 0.347 M to catter the need of healthcare facilities amd RFW.
28 | 3.1 | Communication campaign & GRM | C | Non Consulting Services Comp-3 | Hiring of Non Consultancy Firm and/or Procurent from Firm/Supplier | Haripur, Nowshera, Peshawar & Swabi | 30012000 | 20008000 | 25010000 | 25010000 | Consultancy Firm along with supervision of PMU | 10 | A037- Consultancy & Contractual work | 100040000 | 10004000 | 351017.5439
29 | 4.1 | Reconstrcution and Rehabilitation of Healthcare facilities of Flood affected Distrcits | E | Civil Works | Hiring of Design and Supervision Firm/Construction Firm/Supplier | 16 additional Flood affected Districts |  | 456000000 | 684000000 | 1140000000 | Consultancy Firm along with supervision of PMU | 10 | A037- Consultancy & Contractual work | 2280000000 | 228000000 | 8000000 | In PC-1 in year three total USD 4.8 M allocated, however, the amount have been decreased to 1.4 M to catter the need of healthcare facilities amd RFW.
30 | 4.2 | Furniture, Equipement & other supplies for Flood Affected Healthcare Fcailities | E | Goods (Tangible and Intangible) | Procurement of Medicines, Equipments, Consumable and other supplies | 16 additional Flood affected Districts |  |  | 228000000 | 342000000 | Consultancy Firm along with supervision of PMU | 10 | A-09 Expenditure on acquiring of Physical Assets | 570000000 | 57000000 | 2000000
31 | 4.3 | Human Resource for Flood Component | E | Consulting Services | Hiring of Consultancy Individuals | 16 additional Flood affected Districts | 4275000 | 4275000 | 4275000 | 4275000 | PMU KP HCIP | 12 | A037- Consultancy & Contractual work | 17100000 | 1425000 | 60000
|  | Total in PKR |  |  |  |  | 2063875264.125 | 5504198964.125 | 8917594864.125 | 3996491364.125 |  |  |  | 20482160456.5 |  | 71867229.6719
|  | Total in USD |  |  |  |  | 7241667.5934 | 19312978.8215 | 31289806.5408 | 14022776.7162
85
10
7
3
71.8

## Annex-A
Annexure "A" HR/Salary Component
S.# | Designation | BPS/MP | No. | Salary Per Month | Amount (PKR) | FY 22 | FY 23 | FY 24 | FY 25 | Total | Amount USD (PKR 285 = 1 USD)
1 | Project Director | 19 | 1 | 800000 | 9600000 | 10080000 | 10584000 | 11113200 | 11668860 | 53046060 | 33684.2105
2 | Deputy Project Director | 18 | 1 | 600000 | 7200000 | 7560000 | 7938000 | 8334900 | 8751645 | 39784545 | 25263.1579
3 | Financial Management Specialist | Market Based Salary Package | 1 | 550000 | 6600000 | 6930000 | 7276500 | 7640325 | 8022341.25 | 36469166.25 | 23157.8947
5 | Procurement Specialist |  | 1 | 550000 | 6600000 | 6930000 | 7276500 | 7640325 | 8022341.25 | 36469166.25 | 23157.8947
6 | M&E Specialist |  | 1 | 550000 | 6600000 | 6930000 | 7276500 | 7640325 | 8022341.25 | 36469166.25 | 23157.8947
7 | MIS Officer | 17 | 1 | 160000 | 1920000 | 2016000 | 2116800 | 2222640 | 2333772 | 10609212 | 6736.8421
8 | Office Assistants | 16 | 2 | 80000 | 1920000 | 2016000 | 2116800 | 2222640 | 2333772 | 10609212 | 6736.8421
9 | Accountant | 16 | 1 | 82000 | 984000 | 1033200 | 1084860 | 1139103 | 1196058.15 | 5437221.15 | 3452.6316
10 | Receptionist | 7 | 1 | 40000 | 480000 | 504000 | 529200 | 555660 | 583443 | 2652303 | 1684.2105
11 | Driver | 6 | 4 | 35000 | 1680000 | 1764000 | 1852200 | 1944810 | 2042050.5 | 9283060.5 | 5894.7368
12 | Naib Qasid | 3 | 3 | 35000 | 1260000 | 1323000 | 1389150 | 1458607.5 | 1531537.875 | 6962295.375 | 4421.0526
13 | Cleaner/Sweeper | 3 | 1 | 35000 | 420000 | 441000 | 463050 | 486202.5 | 510512.625 | 2320765.125 | 1473.6842
14 | Security Guard/Chowkidar | 3 | 2 | 35000 | 840000 | 882000 | 926100 | 972405 | 1021025.25 | 4641530.25 | 2947.3684
| Total |  | 20 |  | 46104000 | 48409200 | 50829660 | 53371143 | 56039700.15 | 254753703.15 | 161768.4211
| PC-I Approved Cost for FY 2024-25 | 34040490
| Total Cost for PSC Approval | 46104000
| Difference is Charged from TA Salary Cost | -12063510

## Annex-B
Annexure "B" Non Salary Component
S.No. | IUFR Code | Operational Heads | Accounts Code | Amount (PKR) | Amount (USD) (PKR 285 = 1 USD) | Remarks
1 | IOC | Telephone Charges | A03202 | 300000 | 1052.6316 | PMU official telephone charges for the Period of July-2024 to June-2025
2 | IOC | Gas Charges | A03301 | 300000 | 1052.6316 | PMU office gas charges for the Period of July-2024 to June-2025
3 | IOC | Electricity Charges | A03303 | 5000000 | 17543.8596 | PMU office electricity charges for the Period of July-2024 to June-2025
4 | IOC | Stationary Charges | A03901 | 1500000 | 5263.1579 | PMU office stationary charges for the Period of July-2024 to June-2025
5 | IOC | Printing Charges | A03902 | 1000000 | 3508.7719 | PMU Printing and Stationary charges for the period of July-2024 to June-2025
6 | IOC | POL Charges | A03807 | 20000000 | 70175.4386 | PMU 07 No. Vehicle POL charges for local and Field monitoring visits of 04 Districts for the period July-2024 to June-2025
7 | IOC | Conveyance | A03808 | 200000 | 701.7544 | PMU staff Local official visit to line departments for July-2024 to June-2025
8 | IOC | Misc Allowances (Retirement benefit and death compensatory, GP Fund and benovellent fund) | A011 | 1000000 | 3508.7719 | Deposit of necessary deductions of the deputationist in Government Treasury
9 | IOC | Medical Charges | A01274 | 200000 | 701.7544 | Reimbursement of Medical treatment to KP-HCIP Staff after completion of codal formalities.
10 | IOC | Transportation of Vehicle/Goods | A03806 | 3500000 | 12280.7018 | Transportation of Medicines and other stock to Warehouse and further distribution to Health facilities located in District Peshawar, Nowshera, Swabi and Haripur.
11 | IOC | TA/DA | A03805 | 5000000 | 17543.8596 | Hoteling stay, per diem, travelling and daily allowance payment to PMU/visiting staff for official visits for the period of July-2024 to June-2025
12 | IOC | Repair and Maintenance of Vehicle | A13001 | 500000 | 1754.386 | Monthly service/maintenance charges for 04 No. vehicles of PMU for the period July-2024 to June-2025
13 | IOC | Consumable Materials and Supplies | A03970 | 2050000 | 7192.9825 | Monthly PMU office contingencies charges like tissue papers, senitoizer etc or other office maint. Charges for the peroid of July-2024 to June-2025
14 | IOC | Rent and Maintenance of Office | A03402 | 10000000 | 35087.7193 | Monthly PMU office rent @ Rs. 450,000/- per month, including minor repair work of the rented building for the period of July-2024 to June-2025. Hence due to insufficient budget the amount of Rs. 5,000,000/- may be reappropriated from (-) Rent and Maintenance of Office to (+) POL Charges
15 | IOC | Advertising and Newspaper Subscription | A03905 | 50000 | 175.4386 | Monthly PMU office Newspaper and journals etc charges for the period of July-2024 to June-2025
16 | IOC | Repair of Equipment | A13101 | 500000 | 1754.386 | This includes PMU office monthly service or maintenance charges for equipments like Printers, Photocopiers, Air conditioners etc for the period of July-2024 to June-2025
17 | IOC | Computer Software & Accessories | A09202 | 200000 | 701.7544 | Purchase of various kind of softwares for HRM, FMIS etc for PMU office for the current financial year
18 | Goods (Tangible and Intangible) | Purchase of Furniture & Fixtures | A09701 | 1000000 | 3508.7719 | Allocation as per PC-I for the current year and procurement will be made as and when required after completion of codal formalities
19 | Goods (Tangible and Intangible) | Purchase of Computers | A09201 | 1000000 | 3508.7719 | Allocation as per PC-I for the current year and procurement will be made as and when required after completion of codal formalities
20 | Goods (Tangible and Intangible) | Purchase of Plant and Machinery/Equipments | A09601 | 1000000 | 3508.7719 | Allocation as per PC-I for the current year and procurement will be made as and when required after completion of codal formalities
21 | Goods (Tangible and Intangible) | Purchase of Vehicle | A09601 | 2600000 | 9122.807 | Purchase of Motorcycle 70 CC for Local duties as in FY 2023-24 these were not purchased due to late approval of revised PC-I and restructuring paper by World Bank. Moroever, a suzuki bolan is added for transport purpose
22 | Traning and Workshop | Conferences/Seminars/Workshops/Symposia | A03903 | 4700000 | 16491.2281 | Meeting of Mission/officials for progress and review of the project for the period of July-2024 to June-2025. Hence due to insufficient budget the amount of Rs. 600,000/- may be reappropriated from (-) Conference/Seminars/Workshops/Symposia to (+) Purchase of Vehicle
23 | Non Consulting Services | Advertisement and Promotional activities | A03907 | 3000000 | 10526.3158 | Advertisement of rutine activities through information department and conducting of mass awareness campaign through print and electronic media charges for the period of July-2024 to June-2025. Hence due to insufficient budget the amount of Rs. 2,000,000/- may be reappropriated from (-) Advertisement and Promotional Activities to (+) POL Charges
| IOC | Rental Vehicle for PMU |  | 10000000 | 35087.7193
|  | Total |  | 74600000 | 261754.386

## Annex-C
Annexure "C" District wise list of Health Facilities
S.No. | Name | District
DISTRICT PESHAWAR
BASIC HEALTH UNIT
S.No. | Name | District
1 | BHU Adizai | Peshawar
2 | BHU Barber Uppazai | Peshawar
3 | BHU Bazid Khel | Peshawar
4 | BHU Budhai | Peshawar
5 | BHU Chamkani | Peshawar
6 | BHU Charperiza | Peshawar
7 | BHU Darmangi | Peshawar
8 | BHU Faqir Killi | Peshawar
9 | BHU Fida Abad | Peshawar
10 | BHU Governor House | Peshawar
11 | BHU Gulshan-E-Rehman | Peshawar
12 | BHU Hazar Khawani | Peshawar
13 | BHU Jhagra | Peshawar
14 | BHU Jogani | Peshawar
15 | BHU Kharaki | Peshawar
16 | BHU Shagi Bala(Khatki) | Peshawar
17 | BHU Khazana | Peshawar
18 | BHU Kafoor Dheri | Peshawar
19 | BHU Lala Killi | Peshawar
20 | BHU Maira Surizai | Peshawar
21 | BHU Masho Khel | Peshawar
22 | BHU Maryam Zai | Peshawar
23 | BHU Mashogagar | Peshawar
24 | BHU Nasir Bagh | Peshawar
25 | BHU Mandra Khel(Pajagi) | Peshawar
26 | BHU Pakha Ghulam | Peshawar
27 | BHU Palosai | Peshawar
28 | BHU Phandoo Payan | Peshawar
29 | BHU Pishta Khara | Peshawar
30 | BHU Saeed Abad | Peshawar
31 | BHU Sarband | Peshawar
32 | BHU Tarai Payan(Shaqi H.K) | Peshawar
33 | BHU Sheikh Mohammadi | Peshawar
34 | BHU Sherkera | Peshawar
35 | BHU Sufaid Dheri | Peshawar
36 | BHU Surizai Bala | Peshawar
37 | BHU Tela Band | Peshawar
38 | BHU Urmer Payan | Peshawar
39 | BHU Wadpaga | Peshawar
40 | BHU Gul Bella | Peshawar
41 | BHU Budhani | Peshawar
42 | BHU Urmer Miana | Peshawar
43 | BHU Chaghar Matti | Peshawar
44 | BHU Dalazak | Peshawar
45 | BHU Sango Landi | Peshawar
46 | BHU Aza Khel | Peshawar
47 | BHU Mathra | Peshawar
RURAL HEALTH CENTERS
1 | RHC Regi | Peshawar
2 | RHC Putwar | Peshawar
3 | RHC Takht Abad | Peshawar
Secondary Care Hospitals
S.No | Name of Health Facility | Category
1 | Molve Je Hospital Peshawar | C
2 | Sifwat Ghayur Hospital, Peshawar | C
3 | Police and Services Hospital Peshawar | C
4 | Emergency Satelite Centre Nahaqi | C
5 | Type-D Hospital Mathani | D
6 | Cat-D Hospital Badaber | D
7 | Cat-D Hosital Gara Tajik | D
8 | Govt: Maternity Hospital, Peshawar | D
DISTRICT NOWSHERA
BASIC HEALTH UNIT
1. | BHU Adamzai | Nowshera
2. | BHU Aman Kot | Nowshera
3. | BHU Chashmai | Nowshera
4. | BHU Badrashi | Nowshera
5. | BHU Behram Killay | Nowshera
6. | BHU Dag Basud | Nowshera
7. | BHU Dagai | Nowshera
8. | BHU Inzurai | Nowshera
9. | BHU Manduri | Nowshera
10. | BHU Jalozai | Nowshera
11. | BHU Jehangira | Nowshera
12. | BHU Khush Maqam | Nowshera
13. | BHU Manai | Nowshera
14. | BHU Misri Banda | Nowshera
15. | BHU Mohib Banda | Nowshera
16. | BHU Mughal Kai | Nowshera
17. | BHU Pahari Kati Khel | Nowshera
18. | BHU Pir Sabak | Nowshera
19. | BHU Rashakai | Nowshera
20. | BHU Saleh Khana | Nowshera
21. | BHU Shaidu | Nowshera
22. | BHU Sheikhai | Nowshera
23. | BHU Spin Khak | Nowshera
24. | BHU Taru Jabba | Nowshera
25. | BHU Wazir Garhi | Nowshera
26. | BHU Mama Khel | Nowshera
27. | BHU Banda Mullahan | Nowshera
28. | BHU Gandheri | Nowshera
29. | BHU Azakhel | Nowshera
RURAL HEALTH CENTERS
1 | RHC Akbar Pura | Nowshera
2 | RHC Kheshki | Nowshera
3 | RHC Khair Abad | Nowshera
4 | RHC Pir Pai | Nowshera
5 | RHC Nizam Pur | Nowshera
6 | RHC Kahi | Nowshera
Secondary Care Hospitals
S.No | Name of Health Facility | Category
1 | Categry -D Hospital Kaka Sahib | D
2 | Categry -D Hospital Akora Khattak | D
3 | Categry -D Hospital Manki Sharif | D
4 | Categry -D Hospital Dak Ismail Khel | D
5 | Type-D Hospital Nizampur | D
DISTRICT SWABI
BASIC HEALTH UNIT
1. | BHU Dagai | Swabi
2. | BHU Jalbai | Swabi
3. | BHU Jalsai | Swabi
4. | BHU Lahore Poray | Swabi
5. | BHU Lahore Rapory | Swabi
6. | BHU Mangolchai | Swabi
7. | BHU Mankai | Swabi
8. | BHU Qadra | Swabi
9. | BHU Shah Mansoor | Swabi
10. | BHU Tarakai | Swabi
11. | BHU Bachai | Swabi
12. | BHU Parmoli(Bahadar Abad) | Swabi
13. | BHU Baja | Swabi
14. | BHU Dhobian | Swabi
15. | BHU Fazal Abad | Swabi
16. | BHU Gandaf | Swabi
17. | BHU Gani Chatra | Swabi
18. | BHU Ismaila | Swabi
19. | BHU Jehangira | Swabi
20. | BHU Kalabat | Swabi
21. | BHU Mian Killi | Swabi
22. | BHU Maini | Swabi
23. | BHU Sadri Jadid | Swabi
24. | BHU Sard China | Swabi
25. | BHU Zaida | Swabi
26. | BHU Zarobi | Swabi
27. | BHU Adina | Swabi
28. | BHU Beta Kara | Swabi
29. | BHU Dheri Zakria | Swabi
30. | BHU Check Nodeh | Swabi
31. | BHU Punj Pir | Swabi
32. | BHU Salim Khan | Swabi
33. | BHU Tando Kohi | Swabi
34. | BHU Yaqoobai | Swabi
35. | BHU Gabasni | Swabi
RURAL HEALTH CENTERS
1 | RHC Marghuz | Swabi
2 | RHC Sheikh Jana | Swabi
3 | RHC, Ambar Kunda | Swabi
4 | RHC, Kotha | Swabi
5 | RHC, Tordher | Swabi
6 | RHC, Shewa | Swabi
7 | RHC Kabganai | Swabi
8 | RHC Janda | Swabi
9 | RHC Beka | Swabi
Secondary Care Hospitals
S.No | Name of Health Facility | Category
1 | Categry -C Hospital Topi | C
2 | THQ Lahor | C
3 | Categry -D Kalu khan | D
4 | Categry -D Yar Hussain | D
DISTRICT HARIPUR
BASIC HEALTH UNIT
1. | BHU Amgah | Haripur
2. | BHU Bandi Sher Khan | Haripur
3. | BHU Bagra | Haripur
4. | BHU Barakot | Haripur
5. | BHU Beer | Haripur
6. | BHU Burg | Haripur
7. | BHU Dartian | Haripur
8. | BHU Dhenda | Haripur
9. | BHU Dingi | Haripur
10. | BHU Gadwalian | Haripur
11. | BHU Ghumanwan | Haripur
12. | BHU Gali Amazi | Haripur
13. | BHU Hattar | Haripur
14. | BHU Jattipind | Haripur
15. | BHU Job | Haripur
16. | BHU Kalinger | Haripur
17. | BHU Kangra Colony | Haripur
18. | BHU Kariplian | Haripur
19. | BHU Kakotri | Haripur
20. | BHU Kohi Nara | Haripur
21. | BHU Koklian Peeran | Haripur
22. | BHU Kotohara | Haripur
23. | BHU Kundi | Haripur
24. | BHU Luder Mong | Haripur
25. | BHU Chantry | Haripur
26. | BHU Manakrai | Haripur
27. | BHU Meelam | Haripur
28. | BHU Mirpur Kahal | Haripur
29. | BHU Mong | Haripur
30. | BHU Najafpur | Haripur
31. | BHU Nullah | Haripur
32. | BHU Muslim Abad | Haripur
33. | BHU Pannian | Haripur
34. | BHU Salam Khund | Haripur
35. | BHU Sarai Saleh | Haripur
36. | BHU Sikandarpur | Haripur
37. | BHU Tofkian | Haripur
38. | BHU Shah Muhammad | Haripur
39. | BHU Buttgali | Haripur
40 | BHU Kaneeri | Haripur
RURAL HEALTH CENTERS
1 | RHC Kot Najeebullah | Haripur
2 | RHC Seri Kot | Haripur
3 | RHC Nara Amazai | Haripur
4 | RHC Hali | Haripur
5 | RHC Kalinger | Haripur
Secondary Care Hospitals
S.No | Name of Health Facility | Category
1 | Categry -C Hospital Kalabat | C
2 | Type-D Hospital Ghazi | D
3 | Type-D Hospital Kanpur | D
4 | Type-D Hospital Serei Niamat Khan | D

## Annex-C2
Detail of Activity of Component 1.1 i.e. Infrastructure & Equipment Upgradation of BHUs, 24/7 BHUs and RHC. (Civil works, Solar power system, Furniture and Equipment)
Activity Name | Per facility as per proposed design | Estimated Amount in M in PKR per facility as per proposed design | Amoun in M in USD per facility | Amount in M in USD in total | Remarks
Construction Cost for 60 BEmONC | 72 M per Facility @ of 9000 sq-ft estimation for civil work. Approx 8000 sq-ft covered area is proposed as per guidence of Bank infra Team specialist, in light to international standards for BEmONC center | 72 | 0.25263 | 15.1579 | The Cost of only BEmONC is added, the design of which will be finalized before 20th may and Costrcution of all these ccenters will be started from 10th Aug 24. There will be 10 Months to complete which is achivebale
Solarization Cost | BHU = 1.5 M PKR (5KV soalr system) | 1.5 | 0.0052632 | 0.47368 | There is no need to wait for contsruction, if Bnak Teams apporve this activty the contract can be awarded till Sep-24 and six (06) months time will be given to firm to complete the solarization. The work will be completed before April 25.
| RHC = 5 M PKR (30 KV solar System) | 6 | 0.021053 | 0.48421
| BEmONC = 5 M PKR (20 soalr KV System) | 5 | 0.017544 | 1.0526
Equipment Cost For 60 BEmONC | 15 M per Fcaility | 15 | 0.052632 | 3.1579 | There is no need to wait for contsruction, if Bnak Teams apporve this activty the contract can be awarded till Sep-24 and three (03) months time will be given to firm to complete. The work will be completed before Feb 25.
Equipment Cost For 25 RHCs and some BHUs to be converted to BEmONC | 10 M Per Facility | 10 | 0.035088 | 2.1053 | There is no need to wait for contsruction, if Bnak Teams apporve this activty the contract can be awarded till Sep-24 and three (03) months time will be given to firm to complete. The work will be completed before Feb 25.
| Grand Total of activity in USD in M |  |  | 22.4316 | The total amount allocated in PC-1 for this activity is 23 M USD

## Annex-D
Annexure "D" Technical Assistance to support KP-HCIP Health PMU (PKR 285 = 1 USD)
S.# | Designation | No. | Salary Per Month | Amount (PKR) | Amount USD (PKR 285 = 1 USD)
1 | Enviromental Specialist | 1 | 400000 | 4800000 | 16842.1053
2 | Social Safeguard Specialist | 1 | 400000 | 4800000 | 16842.1053
3 | Gender Specialist | 1 | 400000 | 4800000 | 16842.1053
4 | Infrastrcuture Specialist | 1 | 400000 | 4800000 | 16842.1053
5 | Communication Specialist | 1 | 400000 | 4800000 | 16842.1053
6 | Resident Engineer | 1 | 250000 | 3000000 | 10526.3158
7 | Assistant Resident Engineer | 2 | 200000 | 4800000 | 16842.1053
8 | Refferal Guideline Specialist | 1 | 300000 | 4375822.5 | 15353.7632
10 | Acountant | 2 | 200000 | 4800000 | 16842.1053
11 | Procurement TA (Procurement/Pharmacist/ Biomedical Engineer/Logistic etc.) | 4 | 100000 | 4800000 | 16842.1053
12 | Health Specialist | 1 | 400000 | 4800000 | 16842.1053
13 | Any Other (Health Promoting School TA, QoC TA and etc.) | 5 |  | 13577634 | 47640.8211
| Total | 21 |  | 64153456.5 | 225099.8474
Any other TA as required for the support of PMU with approval of World Bank and Project Steering Committee. The amount to be paid to TA shall not be fixed as mentioned above and it will decided on case to case basis.
| PC-I Approved Cost for FY 2024-25 |  | 76216967
| Total Cost for PSC Approval |  | 64153456.5
| Difference is Charged to PMU Salary Cost |  | 12063510.5

## Annex-E
Annexure "E" District wise list of Health Facilities
Summary of Flood affected Districts
| Name of Health Facility | Type of Damage
S# | District | Refugee Population | Completely Damaged | Partially Damaged | Grand Total
1 | Abbottabad | 14075 | 4 | 6 | 10
2 | Charsadda | 17284 | 0 | 4 | 4
3 | Chitral Lower | 0 | 0 | 9 | 9
4 | Chitral Upper | 6231 | 1 | 5 | 6
5 | D. I. Khan | 8261 | 3 | 19 | 22
6 | Dir Lower | 34159 | 0 | 7 | 7
7 | Dir Upper | 1888 | 0 | 15 | 15
8 | Karak | 1417 | 0 | 13 | 13
9 | Kohistan Lower | 11 | 4 | 3 | 7
10 | Kohistan Upper | 0 | 1 | 4 | 5
11 | KolaiPalas (Kohistan) | 0 | 0 | 3 | 3
12 | Kurram Upper | 7 | 0 | 1 | 1
13 | LakkiMarwat | 9085 | 2 | 7 | 9
14 | Nowshera | 86972 | 0 | 4 | 4
15 | Shangla | 3 | 0 | 5 | 5
16 | Swat | 1746 | 0 | 15 | 15
17 | Tank | 1079 | 0 | 23 | 23
| Grand Total | 182218 | 15 | 143 | 158
Departmental Flood Response Plan
Damages Report Assessment by Health Department
S# | Damages reported District Wise | Nomenclature Infra Damage (Duly verified by Department) |  | Total verified damage reported by | Remarks
1 | Abbottabad | 1 | CD Harikhatar | DHO Abbottabad | Completely Damaged
|  | 2 | CD Chehr |  | Completely Damaged
|  | 3 | CD Khanna |  | Partially Damaged
|  | 4 | CD Chandu Maira |  | Completely Damaged
|  | 5 | CD Kothwal |  | Partially Damaged
|  | 6 | CD Kanthiall |  | Partially Damaged
|  | 7 | CD Sialkot |  | Completely Damaged
|  | 8 | BHU Harlan |  | Partially Damaged
|  | 9 | BHU Banda Pir Khan |  | Partially Damaged
|  | 10 | BHU Kalu Maira |  | Partially Damaged
2 | Shangla | 1 | RHC Karora | DHO Shangla | Partially Damaged
|  | 2 | BHU Towa |  | Partially Damaged
|  | 3 | CD Mian Kalay |  | Partially Damaged
|  | 4 | CD Ganshall |  | Partially Damaged
|  | 5 | BHU Shahlizara |  | Partially Damaged
3 | Nowshera | 1 | BHU Mohib Banda | DHO Nowshera | Partially Damaged
|  | 2 | BHU Pir Sabaq |  | Partially Damaged
|  | 3 | BHU Banda Mullahan |  | Partially Damaged
|  | 4 | RHC Pirpai |  | Partially Damaged
4 | D. I. Khan | 1 | BHU Rasheed | DHO D.I Khan | Completely Damaged
|  | 2 | BHU Mat |  | Completely Damaged
|  | 3 | BHU Rori |  | Completely Damaged
|  | 4 | Type D Hospital Parova |  | Partially Damaged
|  | 5 | RHC Kirri Shamozai |  | Partially Damaged
|  | 6 | BHU Saggu |  | Partially Damaged
|  | 7 | BHU Jabbar wala |  | Partially Damaged
|  | 8 | BHU Shorkot |  | Partially Damaged
|  | 9 | BHU Budh |  | Partially Damaged
|  | 10 | BHU Fateh |  | Partially Damaged
|  | 11 | BHU Darabankhurd |  | Partially Damaged
|  | 12 | BHU Marha |  | Partially Damaged
|  | 13 | BHU Mangal |  | Partially Damaged
|  | 14 | BHU Mirbazi |  | Partially Damaged
|  | 15 | BHU Takwarah |  | Partially Damaged
|  | 16 | CD Roman Kot |  | Partially Damaged
|  | 17 | CD Girsal |  | Partially Damaged
|  | 18 | CD Diyal |  | Partially Damaged
|  | 19 | CD GaraBakhtiar |  | Partially Damaged
|  | 20 | CD GaraMuhabat |  | Partially Damaged
|  | 21 | CD Hatala |  | Partially Damaged
|  | 22 | SHC KotTagga |  | Partially Damaged
5 | Dir Lower | 1 | RHC Khal | DHO Dir Lower | Partially Damaged
|  | 2 | RhCGulabad |  | Partially Damaged
|  | 3 | Cat D Hospital Talash |  | Partially Damaged
|  | 4 | BHU Pingal |  | Partially Damaged
|  | 5 | BHU Tawda China |  | Partially Damaged
|  | 6 | BHU Luqman Banda |  | Partially Damaged
|  | 7 | BHU Otala |  | Partially Damaged
6 | Dir Upper | 1 | Category “C” Hospital Wari | DHO Dir Upper | Partially Damaged
|  | 2 | Category “D” Hospital Patrak |  | Partially Damaged
|  | 3 | RHC NehagBandi |  | Partially Damaged
|  | 4 | RHC Sheringal |  | Partially Damaged
|  | 5 | BHU Guwaldai |  | Partially Damaged
|  | 6 | BHU Doag Dara |  | Partially Damaged
|  | 7 | BHU Barikot |  | Partially Damaged
|  | 8 | BHU Qulandi |  | Partially Damaged
|  | 9 | BHU Dobando |  | Partially Damaged
|  | 10 | BHU Hayagay |  | Partially Damaged
|  | 11 | BHU Nasir Abad |  | Partially Damaged
|  | 12 | BHU Daskor |  | Partially Damaged
|  | 13 | BHU Darora |  | Partially Damaged
|  | 14 | CD Usheri |  | Partially Damaged
|  | 15 | CD Beyar |  | Partially Damaged
7 | Tank | 1 | SHC Daraki | DHO Tank | Partially Damaged
|  | 2 | BHU Mumraiz Pathan |  | Partially Damaged
|  | 3 | BHU Kot Allah Dad |  | Partially Damaged
|  | 4 | BHU Cheena |  | Partially Damaged
|  | 5 | BHU Ranawal |  | Partially Damaged
|  | 6 | BHU GaraBalouch |  | Partially Damaged
|  | 7 | BHU Chadhara |  | Partially Damaged
|  | 8 | BHU KOt Musa |  | Partially Damaged
|  | 9 | BHU Dabara |  | Partially Damaged
|  | 10 | BHU GaraShada |  | Partially Damaged
|  | 11 | BHU Sheikh Sultan |  | Partially Damaged
|  | 12 | BHU Kot Hakim |  | Partially Damaged
|  | 13 | BHU CheesanKach |  | Partially Damaged
|  | 14 | BHU Kirri Haider |  | Partially Damaged
|  | 15 | BHU Shah Alam |  | Partially Damaged
|  | 16 | BHU Pai |  | Partially Damaged
|  | 17 | RHC Gomal Bazar |  | Partially Damaged
|  | 18 | CD Jaffar Abad |  | Partially Damaged
|  | 19 | BHU Shadi Khel |  | Partially Damaged
|  | 20 | BHU andari |  | Partially Damaged
|  | 21 | BHU Warooki |  | Partially Damaged
|  | 22 | Type D Hospital Amma Khel |  | Partially Damaged
|  | 23 | RHC Gul Imam |  | Partially Damaged
8 | Swat | 1 | BHU Mashkomai | DHO Swat | Partially Damaged
|  | 2 | BHU Bara Samai |  | Partially Damaged
|  | 3 | BHU Rahatkot |  | Partially Damaged
|  | 4 | RHC Devlai |  | Partially Damaged
|  | 5 | BHU Qamber |  | Partially Damaged
|  | 6 | BHU Islampur |  | Partially Damaged
|  | 7 | BHU Chail |  | Partially Damaged
|  | 8 | BHU Odigram |  | Partially Damaged
|  | 9 | BHU Tamgha |  | Partially Damaged
|  | 10 | BHU Gabral |  | Partially Damaged
|  | 11 | CD Parrow |  | Partially Damaged
|  | 12 | RHC Khazana |  | Partially Damaged
|  | 13 | BHU Sher Palam |  | Partially Damaged
|  | 14 | CD Nawa Kalay |  | Partially Damaged
|  | 15 | CD Osho |  | Partially Damaged
9 | KolaiPalas Kohistan | 1 | TBC Ghazi Abad | DHO KolaiPalas Kohistan | Partially Damaged
|  | 2 | BHU Sharied |  | Partially Damaged
|  | 3 | BHU Ber Sheryal |  | Partially Damaged
10 | Chitral Upper | 1 | BHU Khoth | DHO Chitral Upper | Completely Damaged
|  | 2 | BHU Sangush |  | Partially Damaged
|  | 3 | BHU Kosht |  | Partially Damaged
|  | 4 | CD Riri |  | Partially Damaged
|  | 5 | CD Lonkow |  | Partially Damaged
|  | 6 | CD Kushum |  | Partially Damaged
11 | Kurram | 1 | CD Mulla Bagh | DHO Kurram | Partially Damaged
12 | Chitral Lower | 1 | BHU Nagar | DHO Chitral Lower | Partially Damaged
|  | 2 | BHU Tar (Shishikoh) |  | Partially Damaged
|  | 3 | RHC Kaghuzi |  | Partially Damaged
|  | 4 | BHU Goboor |  | Partially Damaged
|  | 5 | BHU Moroi |  | Partially Damaged
|  | 6 | BHU Bumborate |  | Partially Damaged
|  | 7 | BHU Shoghore |  | Partially Damaged
|  | 8 | CD Pursat( Shishikoh) |  | Partially Damaged
|  | 9 | BHU Kesu |  | Partially Damaged
13 | Karak | 1 | Type C Hospital City Karak | DHO Karak | Partially Damaged
|  | 2 | DHO office Karak |  | Partially Damaged
|  | 3 | CD Kurd Sharif |  | Partially Damaged
|  | 4 | BHU Mona Khel |  | Partially Damaged
|  | 5 | BHU Makoori |  | Partially Damaged
|  | 6 | BHU Khurram |  | Partially Damaged
|  | 7 | BHU Ghundi Mir Khan Khel |  | Partially Damaged
|  | 8 | RHC ShanawaGudikhel |  | Partially Damaged
|  | 9 | BHU DabliLawagher |  | Partially Damaged
|  | 10 | BHU Shamshaki |  | Partially Damaged
|  | 11 | BHU EsakChountra |  | Partially Damaged
|  | 12 | BHU Kando Khel |  | Partially Damaged
|  | 13 | CH Terri |  | Partially Damaged
14 | Charsadda | 1 | CD Agra | DHO Charsadda | Partially Damaged
|  | 2 | BHU Gul Abad |  | Partially Damaged
|  | 3 | BHU Kot |  | Partially Damaged
|  | 4 | CD Kharakai |  | Partially Damaged
15 | LakkiMarwat | 1 | Cat D Hospital Titter Khel | DHO LakkiMarwat | Partially Damaged
|  | 2 | BHU Hati Khan Langer Khel |  | Partially Damaged
|  | 3 | BHU Abdul Khel |  | Partially Damaged
|  | 4 | BHU Shahbaz Khel |  | Partially Damaged
|  | 5 | BHU Gabar Bagh |  | Partially Damaged
|  | 6 | CD Kheru Khel |  | Completely Damaged
|  | 7 | CD Dalo Khel |  | Completely Damaged
|  | 8 | CD Rabnawazwargari |  | Partially Damaged
|  | 9 | CHC Nadar Khan Farid khel |  | Partially Damaged
16 | Kohistan Lower | 1 | BHU MoniKhailbela | DHO Kohistan Lower | Completely Damaged
|  | 2 | BHU Mujgali |  | Partially Damaged
|  | 3 | BHU Banil Qala |  | Completely Damaged
|  | 4 | CD Semo Dara |  | Completely Damaged
|  | 5 | RHC Ranolia |  | Partially Damaged
|  | 6 | BHU DubairBala |  | Partially Damaged
|  | 7 | BHU Jag |  | Completely Damaged
17 | Kohistan upper | 1 | BHU Jashoi | DHO Kohistan Upper | Partially Damaged
|  | 2 | BHU Thoti |  | Completely Damaged
|  | 3 | CD Bari SiglooRichaw |  | Partially Damaged
|  | 4 | BHU Baja |  | Partially Damaged
|  | 5 | BHU Razika |  | Partially Damaged

## Annex1
Annexure "E" List of Cat D Hospital
DISTRICT PESHAWAR
1 | Emergency Satelite Centre Nahaqi | C
DISTRICT NOWSHERA
2 | Categry -D Hospital Akora Khattak | D
DISTRICT SWABI
3 | THQ Lahor | C
DISTRICT HARIPUR
4 | Type-D Hospital Ghazi | D

## AIP till life of project
Head Wise | Accelerated Implementation and Disbursement Plan of KP-HCIP Health Till Life of Project (June 25) | [9 empty] | Proposed cancellation amount | Accelerated Disbursement Plan | Procurement Timelines
| Approved Cost in Old PC-1 |  | Revised PC-1 Cost | [6 empty] | Allocation in PC-1 in USD in Million
Year-wise Financial Phasing (1US$=285 PKR)
Phasing (1US$=156 PKR)
| Approved | Expenditure before June 23 | Budget approved by PSC & WB for FY 2023-24 (PKR) | Total Expenditure expected till June 24 | Total Expenditure expected till Dec-24 | Total Expenditure expected till June-25 | Total Expenditure planned till June-25 | Grand TOTAL allocated in PC-1 | Excess/(Surrender) will be approved by Project Steering Committee
Note: 1. After Dec-2024 no new activity will be added on STEP and all ongoing activities till award of contract is planned to be finalized before November 24. 2. All Activities (Procurement Plan for 2024) already added on STEP for NOL except Infrastructure/Civil Works (the timelines of which are mentioned in the plan below).
[13 empty] | Status of activity | Start Date | Advertisement date | Bid submission date | Technical Evaluation report Finalization | Notification for award of contract | Purchase order/Task Order/Supply Order/Work Order | Supply duration/ Completion date of works | Remarks
BHUs and RHCs survey | 31.2 | 26.56 | 4.62 | 4.62 | 0 | 0 | 31.18 | 31.2 | -0.02 | 0.2 | 0 | All Expenditure made |  | Completed
Provision of Essential Medicines to BHU, RHC, Cat-D & Cat-C of selected districts | 0 | 0 | 380 | 380 | 300 | 390 | 1070 | 570 | 500 | 2 | 0 | All expenditure will be made by Dec 2024, even reapropriation of 500M PKR is planned to be utilzed additionaly to cater need of non availibility of medicines to achieve RF target of PC-1. | Priori Review, Direct Selction Method | This is direct selection from already approved Framework contract of health department. Activity added on STEP |  |  |  |  | 15th May 24 | 30 days delivery time of supply | All expenditure will be made before Dec-24
Provision of Family Planning commodities to BHU, RHC, Cat-D & Cat-C of selected districts | 0 | 0 | 142.5 | 142.5 | 200 | 100 | 442.5 | 171 | 271.5 | 0.6 | 0 | All expenditure will be made by Dec 2024, even reapropriation of 271.5M PKR is planned to be utilzed additionaly to cater need of non availibility of FP Comodities to achieve RF target | Post Review Open: National | 8th May 24 | 10th May 24 | 28th May 24 | Till 6th June 24 | 15th June 24 | 30th June 24 | 30 days delivery time of supply | Supply will be made till 30th July 24
Support to ensure 24/7 BHU, RHC, Cat-D and Cat-C operation | 1048.27 | 0 | 387.6 | 100 | 400 | 400 | 900 | 1140 | -240 | 4 | 2 | 900 M PKR will be required for the rest of the project. 240 M PKR (1140-900) will be reapropriated to othere heads. Support staff detail is mentioned in attached sheets (relevant head name). | Post Review Open: National | 1st April 2024 | 10th May 24 | 30th May | 10th June | 20th June 24 | 10th July 24 | Staff will be provided by firm when and where required | Another way of doing this is advertise the postions instead of hirring through firm by 10th May till 30th May. Longlist the list till 15th June 24 and prepare pool of candidate. Afterwards engage staff from that list when and where required.
Improvement of patient record systems | 384 | 0.74 | 285 | 285 | 284.265 | 0 | 570.005 | 570 | 0.005 | 2 | 0 | All expenditure will be made by Dec 2024 for implementation of DHIS-2 as per annex. | Post Review Open: National | 15th March 24 | 08th May 24 | 3rd June 24 | 19th June 24 | 30th June 24 | 20th Jully | Suppllies to be made within 60 days of Purchase order | Framework Contract will be signed till life of the project.
Hospital waste management for BHU, RHC, Cat-D & Cat-C of selected districts | 585 | 0 | 855 | 250 | 1000 | 250 | 1500 | 1068.75 | 431.25 | 3.75 | 0 | All expenditure will be made by Dec 2024. An amount of 181 M PKR will be reapropriated from other heads. | Prior Review Open: National | 1st March 2024 | 12th May 24 | 6th June 24 | 20th June 24 | 10th July 24 | 30th July 24 | 90-120 days | Payment will be made 25% in advance against guarentee with Supply order. 75% will be paid upon installation November 24.
Strengthening of referral system | 156 | 0 | 71.25 | 71.25 | 71.25 | 0 | 142.5 | 142.5 | 0 | 0.5 | 0 | 142.5 M PKR will be utilized till June-25 | Post Review Open: National | 10th Jan 24 | 10th May 24 | 4th June 24 | 15th June 24 | 5th June 24 | 25th June 24 | Supply will be made in 60 days | There are three component in this activity 1) TA: which is already awarded, 2) Refferal slips through RFQ which will be complted by June 24 and 3) RFB method, the contract will be awarded by 20th June 24.
Strengthening of RMNCH Services through purchase of Ambulances | 682.5 | 0 | 1140 | 1140 | 400 | 120 | 1660 | 1246.9 | 413.1 | 4.375 | 0 | 1659 Total Expenditure is planned as per details mentioned in sheet attached. 413 M PKR additionaly will be reapropriated (1660-1246). All expenditure will be made till June 25. | Priori Review, National: Limited Competition | 1st April 2024 | This is direct selection from already approved Framework contract of health department. Activity added on STEP. under RFQ pre-reciept invoices and qoutation sought, after ToRS were approved by Bank Team. However, Purcahase order even if the process is readvertised, can be issued till 30th May 24. |  |  |  | 3rd June 24 | 4 Month for vehicle Supply and 3 Months for febrication. | There are three type of activities; 1. 1000 M to 1200 M PKR in Advance payment will be made for vehicle by 15th June 24. 2. Febrication Payment will be made once febrication made and inspection done. 3. Call center equipement payment will be made once call center is established i.e. not later than Aug 24.
Outsourcing of lab and pharmaceutical services | 468 | 0 | 106.88 | 0 | 700 | 400 | 1100 | 855 | 245 | 3 | 1 | 1100 M PKR expenditure will be made by June 25. 04 state of the art labs will be established in 04 project distrcits (one each distrcit). Per district per lab cost of lab is estimated to be 300 M and operational cost is 100 M PKR. Addition 245 M PKR will be reapropriated (1100-855) from other heads. | Prior Review Open: National QCBS | 15th April 2024 | 15th April 24 | 10th May 24 EOI to be recived | 25th May 2024, RFP to be issued 21st June 24 RFPs to be recived and evaluated by 5th July 24 | 15th July 24 | 10th Aug 24 | 90 days will be given to firm for establishment of Laboratory services | 04 labs will be established, 01 per distrcits and the rest of the facilities will be linked with it for sample processing etc. All Payments will be made by 30th dec 24.
Outsourcing of security and janitorial services | 156 | 0 | 427.5 | 427.5 | 400 | 600 | 1427.5 | 855 | 572.5 | 3 | 0 | 1427.5 M expenditure is planned till June 25. Addition 572.5 M PKR will be reapropriated (1427.5-855) from other heads. | Post Review Open: National | Contract Awarded | Contract Awarded Ongoing activity | [5 empty] | 2025-06-01
Outsourcing of Government Health facility at Nishtar Abad | 0 | 228.12 | 350 | 300 | 200 | 200 | 928.12 | 1282.499 | -354.379 | 4.5 | 2 | 928.12 M PKR will be utilized till project life (40 M per Month for 18 Months). | Prior Review Open: International QCBS | Contract Awarded | Contract is expected to be awarded by 20th May 24 and activity ongoing. | [5 empty] | 2025-06-01
Health promotion activities (Health Promoting school and WASH activities) | 156 | 2.85 | 196.65 | 100 | 200 | 300 | 602.85 | 199.5 | 403.35 | 0.7 | 0 | All expenditure will be made tll June 24 and additional 502 M PKR will be required and to be reaprorpiated/reallocated. | 100 HPS establishment | Contract Awarded and work will be completed by June 24
[13 empty] | Post Review Open: National RFB for establishment of HPS | 10th May 24 | 15th May 24 | 5th June 24 | 20th June 24 | 5th July 24 | 20th Jully 24 | Work will be completed by June 25 | 50 HPS will be established per month i.e. 12-15 per distrcits to complete total of 700 schoold by June 25.
[13 empty] | Post Review Limited: National RFQ for Hygiene Kit | 08th May 24 | 10th May 24 | 25th May 24 | 30th May 24 | 5th June 24 | 5th June 24 | Supplies will be made before 30th June 24 | The amount of Hygiene Kits is less than 100,000 USD
[13 empty] | Post Review Limited: National RFQ for IEC Material | 1st April 2024 | 10th May 24 | 25th May 24 | 30th May 24 | 5th June 24 | 5th June 24 | Supplies will be made before 30th June 24 | The amount for printing IEC material and booklets is less than 100,000 USD
Infrastructure & Equipment Upgradation of BHUs, 24/7 BHUs and RHC. (Civil works, Solar power system, Furniture and Equipment) | 4485 | 0 | 1168.5 | 100 | 1969 | 3250 | 5319 | 6581.8 | -1262.8 | 23 | 0 | 20 Contracts will be awarded to contractors to complete work in 115 facilities by June 25. The construction work will be started by June 24. The detail is as under; One BHU to be converted to CEmONC will estimatedly cost 40 M PKR, tottaling to 2400 M PKR for 60 facilities. For every constrcution site work 15 % mobilization advance against guarentee will be given to contractor to improve utilization and early completion of project. One BHU Solarization will cost M PKR, totaling to 1510 m PKR. ONE RHC to be converted to CEmONC will estimatedly cost 20 M PKR, tottaling to 500 M PKR. One BHU Solarization will cost 15 M PKR, totaling to 375 m PKR Equipement Cost: Per Facility cost for BEmONC as per sheet attached is 13 M PKR, totalling to 1495 M PKR. All this expenditure will be made by June 25 as the procuremnet list is availible but the equipement will be ordered once constrcution is near to be completed. 1262 M PKR (6581-5319) will be reapropriated to other heads. | Post Review Limited: National RFQ for Equipmemt | 08th May 24 | 10th May 24 | 25th May 24 | 30th May 24 | 5th June 24 | 5th June 24 | Supplies will be made before 30th June 24 | RFQ mode is opted for facilities which have infrastcructure availible and with provision of equipemnet BEmONC services can be started
[13 empty] | Post Review Open: National RFB for Equipement | 10th May 24 | 13th May 24 | 3rd June 24 | 20th June 24 | 5th Aug 24 | 20th Aug 24 | 90 days supply time for Imported Items 45 Days Supply Time for Local Items | It will be framework contract, and supply of equipments will be made as and when the BEmONC constrcution is about to be completed till June 25.
[13 empty] | Post Review Open: National RFB for Works (BEmONC Facility construction) | 15th June | 15th June | 5th Aug 24 | 16th Aug 24 | 30th Aug 24 | 5th Sep 24 | 9 Months will be given to complete work for each package | By 30th May the Deatil design, Drawing and BoQ will be finalized by the firm and till 10th June 24 will approved from bank team There will be six packages each comprising 10 BEmONC.
[13 empty] | Post Review Limited: National RFQ for Works For Packages of Less than 27 M PKR out od 25 RHCs | 30th Aug 24 | 5th Sep 24 | 22nd Sep 24 | 30th Sep 24 | 10th October 24 | 15th October 24 | 7-8 months will be given to complete each package | This is mostly rehabilitation work, so One Package will be comprised of 4-5 RHCs and 7 Months time will be given to contractor to finish work
[13 empty] | Post Review Limited: National RFQ for Equipmemt | 08th May 24 | 10th May 24 | 25th May 24 | 30th May 24 | 5th June 24 | 5th June 24 | Supply and Installation will be made before 30th June 24 | RFQ mode is opted for facilities which are requested by DHOs to be completed at earliest due to electericity breakdown
[13 empty] | RFB Post review National: Open Solarization of All BHUs and RHCs | 10th May24 | 15th May 24 | 5th June 24 | 20th June 24 | 5th Aug 24 | 15th Aug 24 | 6 Months will be given to complete installation of solar systems in all BHUs and RHCs | For 60 BEmONC 24/7 BHUs 10 KV solar system is proposed For 91 Normal BHUs 5 KV System is Proosed For RHC 24/7, 25-30 KV System is proposed
Timelines are as per Gant chart attached at Sheet (Summary of civil works)
Infrastructure & Equipment Upgrading of Category C and D hospital for referral | 714.15 | 0.45 | 800 | 100 | 900 | 1300 | 2300.45 | 2829.2 | -528.75 | 9.927 | 5.057 | 4 Contract will be awarded till June 24 to start constrcution work in one each districts. For every constrcution site work 15 % mobilization advance against guarentee will be given to contractor to improve utilization and early completion of project. The contractor will be bound to work on multiple location with district to complete the work till June 25. Total 2000 M PKR is for constrcution work to be utilized till June 25. Equipement Cost: Per Facility cost for CEmONC as per sheet attached is 30 M PKR, totalling to 660 M PKR. All this expenditure will be made by June 25 as the procuremnet list is availible but the equipement will be ordered once constrcution is near to be completed. 528.75 M PKR savings (2828-2300) will be reapropriated to other heads | Post Review Open: National RFQ For Equipment | Will be done under the framework contract of BHU and RHCs above
[13 empty] | Post Review Open: National RFB for Works | 15th June | 15th June | 5th Aug 24 | 16th Aug 24 | 30th Aug 24 | 5th Sep 24 | 9 Months will be given to complete work for each package | By 30th May the Deatil design, Drawing and BoQ will be finalized by the firm. There will be 04 packages each comprising 01 Cat-D Hospital
[13 empty] | RFB Post review National: Open Solarization of All Cat-C and Cat-D Hospitals | Will be done under solarizatoin Framework Contract of BHU and RHCs above
Timelines are as per Gant chart attached at Sheet (Summary of civil works)
Warehouse establishment for strengthening the supply chain system strengthening | 117 | 0 | 285 | 0 | 250 | 320 | 570 | 570 | 0 | 2 | 0 | The Contruction work will be awarded by Aug 24 and constrcution work will be started on 04 sites to complete by June 25. All Expenditures will be made by June 25. For every constrcution site work 15 % mobilization advance against guarentee will be given to contractor to improve utilization and early completion of project. | Post Review Open: National RFB for Works (04 Warehouse construction) | 10th May 24 | 10th May 24 | 10th June 24 | 25th June 24 | 15th Aug 24 | 25th Aug 24 | 9 Months will be given to complete work for each package | Contract will be awarded on Turn Key Soltution basis for warehouse
Timelines are as per Gant chart attached at Sheet (Summary of civil works)
| 8983.12 | 258.72 | 6600.5 | 3400.87 | 7274.515 | 7630 | 18564.105 | 18113.349 | 450.756 | 63.552 | 10.057
Training of healthcare providers and capacity building of Health Dept staff | 672 | 0 | 285 | 260 | 195 | 400 | 855 | 855 | 0 | 3 |  | 550 Million is planned to be utilized till June 25. 100 M will be utilized on flagship trainings. 250 M PKR already transferred to PHSA for training after NOL from Bank Team. | Post Review Limited: National RFQ for Stationary Items | 12th May 24 | 12th May 24 | 28th May 24 | 6th June 24 | 12th June 24 | 20th June 24 | Supply will be made as per need | The amount for stationary is less than 270 M PKR i.e. less than 100 thousand USD.
[13 empty] | Post Review Limited: National RFQ for Civil Work at PHSA | 15th May 24 | 15th May 24 | 30th May 24 | 10th June 24 | 20th June 24 | 25th June 24 | 60 days will be given to complete the work | The BOQ prepared and amount is less than 100 thousand USD.
[13 empty] | Post Review Limited: National RFQ for IT equipements to stregthen PHSA | 13th May 24 | 13th May 24 | 28th May 24 | 6th June 24 | 12th June 24 | 22nd June 24 | Supply will be made as per need | The amount for IT equipemnt is less than 270 M PKR i.e. less than 100 thousand USD.
[13 empty] | Post Review Limited: National RFQ for Training Material i.e. Manuals etc Printing | 14th May 24 | 14th May 24 | 28th May 24 | 6th June 24 | 12th June 24 | 15th June 24 | Supply will be made as per need | The amount for Training Material, Maunals and other printing material is less than 270 M PKR i.e. less than 100 thousand USD.
| 672 | 0 | 285 | 260 | 195 | 400 | 855 | 855 | 0 | 3
Quality Enhancement | 384 | 0 | 228 | 28 | 400 | 142 | 570 | 570 | 0 | 2 |  | 300 M PKR will be utilized with following details; 120 M PKR will be utilized for quality liscencing and rest 270 M PKR will be utilized till June 25 for quality improvemnet of Healthcare facilities. | Post Review Open: National RFB for Quality Enhancemnet Materials and comodities | 15th May 24 | 15th May 24 | 10th June 24 | 25th June 24 | 10th Aug 24 | 20th Aug 24 | Supply will be made as per need till life of the Project
[13 empty] | Post Review Limited: National RFQ for Qualty of Care tools Printing | 10th May 24 | 10th May 24 | 26th May 24 | 6th June 24 | 10th June 24 | 10th June 24 | Supply will be made till 30th June 24
PMU, Internal Audit, Project M&E, Third Party Monitoring, transportation of goods and warehousing of stock. | 1248 | 92.8 | 91.16 | 91.16 | 250 | 300 | 733.96 | 997.5 | -263.54 | 3.5 |  | 733 M PKR will be utilized for PMU, Internal Audit, Project M&E, Third Party Monitoring, transportation of goods and warehousing of stock till June 263.6 M PKR savings will be reapropriated to other heads |  | Ongoing activities
KP Health Care Commission support (Registration and GIS mapping of all private healthcare establishment across KP) | 50 | 0 | 85.22 | 85.22 | 0 | 0 | 85.22 | 85.22 | 0 | 0.299 |  | On going contract and all expenditure will be made by June 24. | Post Review Activty | Contract Awarded | [6 empty] | 2024-06-01
Support to KP Health Foundation- for Public Private partnership Strengthening | 150 | 13.11 | 49.87 | 49.87 | 79.52 | 0 | 142.5 | 142.502 | -0.002 | 0.5 |  | On going contract and all expenditure will be made by June 25. | Other than procurement | Ongoing activities | [6 empty] | 2024-12-01
TA to support PMU | 0 | 0 | 63.1 | 30 | 50 | 128.705 | 208.705 | 210.36 | -1.655 | 0.738 |  | On going contracts and all expenditure will be made by June 25. | Individual Consultant Hirring Post review | Staff taken on baord and ongoing activties | [6 empty] | 2025-06-01
| 1832 | 105.91 | 517.35 | 284.25 | 779.52 | 570.705 | 1740.385 | 2005.582 | -265.197 | 7.037
Communication campaign & GRM | 312 | 0 | 99 | 30 | 70 | 100 | 200 | 100 | 100 | 0.351 |  | All expenditure will be made by June 25. 100 M will be reapproriated from other heads after due approval of Project Steering Committee | Post review Open: National Hirring of Communication Firm | 1st April 2024 | EOI recived 20th April 24 and Evaluation Completed, RFP will be issued by 10th May | 29th May 24 | 15th June 24 | 25th June | 30th June 24 | Communication Firm Will work till June 25 | 2025-06-01
[13 empty] | Post Review Limited: National RFQ for GRM Boxes and IEC Material Printing | Contract Awarded and Activity Completed
Unallocated | 785 | 0 | 0 | 0 | 0 | 0 | 0 | 285 | -285 | 1 |  | 285 M PKR will be reapropriated to other heads where required.
| 1097 | 0 | 99 | 30 | 70 | 100 | 200 | 385 | -185 | 1.351
Furniture, Equipment & Supplies for Flood Affected Healthcare Facilities | 0 | 0 | 570 | 100 | 470 | 0 | 570 | 570 | 0 | 2 |  | All expenditure can be made till June 24, however waiting for restrcuturing paper approval from WB side. | Procurement of Equipement Priori Review, Direct Selction Method | 10th May 24 | This is direct selection from already approved Framework contract of health department. Activity added on STEP |  |  |  | 10th May | 30 days delivery time of supply | 15th June 24
[13 empty] | Post Review RFB Open: National RFB Procurement of Equipment & Supplies for Flood Affected Healthcare Facilities | 10th May 24 | 13th May 24 | 3rd June 24 | 20th June 24 | 5th Aug 24 | 20th Aug 24 | 90 days supply time for Imported Items 45 Days Supply Time for Local Items | It will be framework contract, and supply of equipments/Supplies will be made to the Flood affected facilities till June 25.
[13 empty] | Post Review Limited: National RFQ for Furnitures | 10th May 24 | 10th May 24 | 30th May 24 | 10th June 24 | 20th June 24 | 25th June 24 | 60 days will be given to complete the work | The demand of Furniture is less than 100,000 USD.
Reconstruction and Rehabilitation of Healthcare facilities of Flood affected Districts | 0 | 0 | 400 | 50 | 1500 | 730 | 2280 | 2280 | 0 | 8 |  | All expenditure can be made till June 25, however waiting for restrcuturing paper approval from WB side. | Post review CQS Open: National Design and Supervision Firm | Contract awarded and firm started working Designs will be provided in Phased manner till 30th Aug 2024. First Phase Detailed Designs will be provided by 10th June. The rest of detailed Timelines are as per Gant chart attached at Sheet (Summary of civil works) | [6 empty] | 2025-06-01
[13 empty] | Post review Limited: National RFQ for Works For Packages of Less than 27 M PKR for Flood affected rehabilitation work of healthcare facilities | 30th June 24 | 30th June 24 | 20th Aug 24 | 30the Aug 24 | 10th Sep 24 | 15th Sep 24 | 7-8 months will be given to complete each package | This is mostly rehabilitation work, so One Package will be comprised of 4-5 RHCs and 7 Months time will be given to contractor to finish work
[13 empty] | Post review Open: National RFB for Works reconstruction work of fully damaged healthcare facilities | 1st Sep 24 | 1st Sep 24 | 20th Sep 24 | 30th Sep 24 | 15th Oct 24 | 25th Oct 24 | 08 Months will be given to complete work for each package | The Detailed designs and BOQ of Final lot is planned to be submitted by 15th Aug 24 and all designs, drawing and BOQ will be apporved from Bank team between 30th June 24 to 20th Aug 24.
| 0 | 0 | 970 | 150 | 1970 | 730 | 2850 | 2850 | 0 | 0.06
| 12584.12 | 364.63 | 8471.85 | 4125.12 | 10289.035 | 9430.705 | 24209.49 | 24207.8 | 0 | 10.06 |  | Amount falling short to complete all activities by end of Project
| 85 | 1.28 | 29.7258 | 14.4741 | 36.1019 | 33.0902 | 84.9456 | 84.9396 | 0 | 85